## SLAQ & LAC
Site-level Assessment Questionnaire (SLAQ) and LHD Activity Checklist (LAC)
Main Contact: EvaluateSNAPEd@ucanr.edu | Link to SLAQs and LACs: https://ucanr.edu/sites/SLAQ/SLAQ_Questionnaires/
Project Manager: Janice Kao (jankao@ucanr.edu)
Other Staff on Project: Carolyn Rider (cdrider@ucanr.edu), Amanda Linares (amlinares@ucanr.edu), Evaluation TA Team (evaluateSNAPEd@ucanr.edu)
Activities | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
SLAQ Administration | bar: Sept to Jun
Collect completed SLAQs from school, OST, ECE, retail within the same timeframe once a year (unless an alternate situation has been agreed upon)
Sites/programs operatingon school year cycle | bar: Aug to Oct; May to Jul
Non-school-based sites | bar: Aug to Jul
Enter and submit completed SLAQs into Survey 123 and receive scores | bar: Aug to Jul
Use SLAQ results and scores to plan your activities. Action plan available here: https://ucanr.edu/sites/slaq/Resources/ | bar: Aug to Jul
LHD Activity Checklist (LAC) Completion
Enter and submit the SLAQ - LHD Activity Checklist (LAC) into Survey 123 once CFHL activities are complete and before end of federal fiscal year | bar: Aug to Oct; May to Jul
SLAQ Reporting
Annually report on SLAQ results in the PEARS PSE module, in the Needs Assessments section. Job aid available here: https://www.cdss.ca.gov/Portals/9/CAFSP/CalFresh/PEARS/PEARS-PSE-NeedsAssessments-JobAid.pdf | bar: Aug to Oct; May to Jul

## OAQ & LAC
School District - Organizational Assessment Questionnaire (OAQ) and LHD Activity Checklist (LAC)
Main Contact: EvaluateSNAPEd@ucanr.edu
Project Manager: Janice Kao (jankao@ucanr.edu, 510-987-0613)
Other Staff on Project: Carolyn Rider (cdrider@ucanr.edu)
Activities | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
Assessment Administration | bar: Sept to Jun
Collect completed OAQs from school districts within the same timeframe annually (unless an alternate situation has been agreed upon). Ensure that WellSAT scores are included on completed OAQ. | bar: Aug to Oct; May to Jul
Enter and submit completed OAQs, including WellSAT scores, into Survey 123 and receive scores | bar: Aug to Oct; May to Jul
Use OAQ results and scores to plan your activities | bar: Aug to Jul
OAQ LAC Completion
Enter and submit the OAQ - LHD Activity Checklist (LAC) into Survey 123 once CFHL activities are complete and before end of federal fiscal year | bar: Aug to Oct; May to Jul
OAQ Reporting
Annually report on OAQ results in the PEARS PSE module, in the Needs Assessments section. Job aid available here: https://www.cdss.ca.gov/Portals/9/CAFSP/CalFresh/PEARS/PEARS-PSE-NeedsAssessments-JobAid.pdf | bar: Aug to Oct; May to Jul

## PEARS
Program Evaluation and Reporting System (PEARS)
Project Manager: Carolyn Rider (cdrider@ucanr.edu, carolyn.rider@cdph.ca.gov)
Main Point of Contact: EvaluateSNAPEd@ucanr.edu
Other Staff on Project: Janice Kao (jankao@ucanr.edu), Evan Talmage (etalmage@ucanr.edu), Nicole Vital (nvital@ucanr.edu), Kaela Plank (krplank@ucanr.edu)
Activities | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept
Training and Technical Assistance
Attend PEARS training as offered by KSU, CDSS, or NPI. | bar: Oct to Sept
Stay informed about PEARS reporting updates via monthly newsletter. | bar: Oct to Sept
Data Entry
Enter all activities targeting SNAP-Ed audience into PEARS PSE, Program Activities, and Indirect Activities module as they are completed. | bar: Oct to Sept
Enter partnership and coalition data into the appropriate modules. | bar: Oct to Sept
Create at least one PSE-related Success Story by the end of the year. | bar: Oct to Sept
Annually report on SLAQ results in the PEARS PSE module, in the Needs Assessments section. Job aid available here: https://ucanr.edu/sites/CDPH_PEARS/Tools_Resources/ | bar: Oct to Dec
Data Quality Assurance We recommend monthly reviews by LHD managers. In addition, LHD managers and staff should review issues flagged by NPI quarterly, in the months marked with bold Xs.
Periodically review data entered by staff and contractors under your supervision. | bar: Oct to Sept
Respond, as needed, to QA/QC emails sent by state reviewers by making appropriate revisions to data in PEARS. | bar: Oct to Sept
Finalize data entry and quality assurance and mark all entries complete (for prior reporting year) | bar: Oct

## Adult Direct Ed Evaluation
Adult Direct Education Evaluation
Project Manager/Main Point of Contact: Amanda Linares (amlinares@ucanr.edu, 916-200-5188)
Activities | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Planning | bar: Sept to Jun; Aug to Sep
Attend Data Collection training (annually) | bar: Sept
Enter Program Activity into PEARS before administering Pre-test Survey | bar: Oct to Aug
Pretesting, Intervention Implementation, Post-testing | bar: Sept to Jun; Aug to Sep
Administer the CalFresh Healthy Living Adult Pre-test Survey before delivering a direct education series of four or more sessions | bar: Oct to Aug
Administer direct education series of four or more sessions over at least four weeks. | bar: Oct to Aug
Administer the CalFresh Healthy Living Adult Post-test Survey after delivering a direct education series of four or more sessions | bar: Oct to Aug
Data Entry | bar: Sept to Jun; Aug to Sep
If online CalFresh Healthy Living Adult surveys were used, there will be no data entry; if paper surveys were used, pre/post-tests should be entered into Survey123 by Aug 31st. | bar: Oct to Aug
End of Year (August 31st) Deliverables | bar: Sept to Jun; Aug to Sep
To Amanda: 1) Confirm receipt of pre/post-tests in Survey123 | bar: Aug

## IOE
Impact Outcome Evaluation (IOE)
Project Manager/Main Point of Contact: Amanda Linares (amlinares@ucanr.edu, 916-200-5188)
Activities | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
Planning | bar: Sept to Jun
Engage intervention site(s); any school or school-based afterschool serving 4th-12th grades | bar: Aug to Sept; May to Jul
Attend EATS administration training | bar: Aug; Jul
Provide Amanda with a completed Planning Worksheet to receive customized EATS online survey links for each site | bar: Aug to Oct; Jul
Prior to Pre-testing
Send home Parent Opt Out Forms 2 weeks prior to pre-testing | bar: Aug to Oct; Jul
Pre-testing
Administer EATS with at least 2 classrooms of students per site (goal = 30 matched pre/post-tests) | bar: Aug to Oct
Intervention Implementation
Conduct intervention | bar: Sept to May
Post-testing
Administer EATS to all students who received the pre-test | bar: Apr to Jun
Data Entry
If EATS online was used, there will be no data entry; if paper surveys were used, pre/post-tests should be entered into the site-specific survey links | bar: Aug to Jun
End of Year (June 30th) Deliverables
To Amanda: 1) Pre/post tests entered online 2) Planning Workshseet with updates and attrition data | bar: Jun