## PEARS
Program Evaluation and Reporting System (PEARS)
Project Manager: Carolyn Rider (cdrider@ucanr.edu)
Main Point of Contact: EvaluateSNAPEd@ucanr.edu
Other Staff on Project: Janice Kao (jankao@ucanr.edu), Evan Talmage (etalmage@ucanr.edu), Nicole Vital (nvital@ucanr.edu), Reka Vasicsek (rvasicsek@ucanr.edu), Summer Cortez (sjcortez@ucanr.edu)
Activities | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct
First Quarter Data Entry & Quality Assurance | Oct: Gray cells denote all months for activity; X denotes a deadline.
Enter all activities targeting SNAP-Ed audience into PEARS PSE, Program Activities, & Indirect Activities modules as they occur. Ensure reporting is current by end of quarter. | bar: Oct to Dec
Enter partnership and coalition participation into the appropriate modules as they occur. Copy ongoing activities from prior year. Ensure reporting is current by end of quarter. | bar: Oct to Dec
Review and resolve issues flagged by NPI for Quarter 1 and update status in Issue File. | bar: Feb to Mar
Second Quarter Data Entry & Quality Assurance | Oct: Gray cells denote all months for activity; X denotes a deadline.
Enter all activities targeting SNAP-Ed audience into PEARS PSE, Program Activities, & Indirect Activities modules as they occur. Ensure reporting is current by end of quarter. | bar: Jan to Mar
Enter partnership and coalition participation into the appropriate modules as they occur and no later than the end of the quarter. Ensure reporting is current by end of quarter. | bar: Jan to Mar
Review and resolve issues flagged by NPI for Quarter 2 and update status in Issue File. | bar: May to Jun
Third Quarter Data Entry & Quality Assurance | Oct: Gray cells denote all months for activity; X denotes a deadline.
Enter all activities targeting SNAP-Ed audience into PEARS PSE, Program Activities, & Indirect Activities modules as they occur. Ensure reporting is current by end of quarter. | bar: Apr to Jun
Enter partnership and coalition participation into the appropriate modules as they occur and no later than the end of the quarter. Ensure reporting is current by end of quarter. | bar: Apr to Jun
Review and resolve issues flagged by NPI for Quarter 3 and update status in Issue File. | bar: Aug to Sept
Fourth Quarter Data Entry & Quality Assurance | Oct: Gray cells denote all months for activity; X denotes a deadline.
Enter all activities targeting SNAP-Ed audience into PEARS PSE, Program Activities, & Indirect Activities modules as they occur. Ensure reporting is complete by end of quarter. | bar: Jul to Oct
Enter partnership and coalition participation into the appropriate modules as they occur and no later than the end of the quarter. Ensure reporting is complete by end of quarter. | bar: Jul to Oct
Review and resolve issues flagged by NPI for Quarter 4 and update status in Issue File. | bar: Sept to Oct
Respond, as needed, to year-end QA/QC emails sent by NPI by making appropriate revisions to data in PEARS. | bar: Oct
Year-End Data Entry & Quality Assurance | Oct: Gray cells denote all months for activity; X denotes a deadline.
Create at least one PSE-related Success Story by the annual reporting deadline. | bar: Oct to Oct
Finalize data entry and quality assurance and mark all entries complete. | bar: Oct to Oct
Respond, as needed, to year-end QA/QC emails sent by NPI so that state data managers can make appropriate revisions to data in PEARS. | bar: Oct

## SLAQ & LAC
Site-level Assessment Questionnaire (SLAQ) and LHD Activity Checklist (LAC)
Main Contact: EvaluateSNAPEd@ucanr.edu
Project Manager: Janice Kao (jankao@ucanr.edu)
Other Staff on Project: Carolyn Rider (cdrider@ucanr.edu), Amanda Linares (amlinares@ucanr.edu), Evaluation TA Team (evaluateSNAPEd@ucanr.edu)
SLAQs and OAQs are for schools, school districts, OST, ECE, and retail sites that are already engaged CFHL partners and have agreed to implement PSE changes.
Gray cells denote typical months for activity; X denotes a deadline.
Activities | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr
SLAQ Administration (schools, ECE, OST, and retail sites)
Determine which sites will need a SLAQ for the upcoming FFY.
Prepare to conduct SLAQs by reviewing protocols and resources. Identify contacts for each site to facilitate SLAQ completion and share site protocols and questionnaires. Updated SLAQs and protocols are released each July for the upcoming FFY.
Collect completed SLAQs, before PSE changes are implemented for the year. They only need to be conducted once within a year.
Enter and submit completed SLAQs into Survey 123 and receive scores. Entries are due Nov 1 for previous FFY. (Example: All FFY 24 entries are due Nov 1, 2024) | bar: Gray cells denote typical months for activity; X denotes a deadline. Nov
Use SLAQ results and scores to plan your activities. Action planning tools are available here: https://ucanr.edu/sites/slaq/Resources/
OAQ Administration (school districts)
Determine which school districts will need an OAQ for the upcoming FFY.
Prepare to conduct OAQs by reviewing protocols and resources; identify contacts for each district to facilitate OAQ completion, share protocols, and check in about the WellSAT. Updated materials are released each July for the upcoming FFY.
Check that a WellSAT has been completed for each district since their last wellness policy update and within the last 3 years. If not, work with district contact(s) to complete WellSAT.
Collect completed OAQs, before PSE changes are implemented for the year. Ensure that WellSAT scores are included on completed OAQs.
Enter and submit completed OAQs into Survey 123 and receive scores. Entries are due Nov 1 for previous FFY. (Example: All FFY 24 entries are due Nov 1, 2024) | bar: Gray cells denote typical months for activity; X denotes a deadline. Nov
Use OAQ results and scores to plan your activities. Action planning tools are available here: https://ucanr.edu/sites/slaq/Resources/
LHD Activity Checklist (LAC) Completion -- 1 LAC per SLAQ and OAQ
Begin completing the LHD Activity Checklist (LAC) to track CFHL activities at each SLAQ site and OAQ district. Updated ACs are released in January each year.
Enter completed LACs into Survey 123 once all your CFHL activities have finished for the year. Entries are due Nov 1 for previous FFY. (Example: All FFY 24 entries are due Nov 1, 2024) | bar: Gray cells denote typical months for activity; X denotes a deadline. Nov
SLAQ Reporting
Report your most recent SLAQ and OAQ results in PEARS (PSE module, Needs Assessments section). Job aid available here: https://www.cdss.ca.gov/inforesources/pears | bar: Gray cells denote typical months for activity; X denotes a deadline. Oct

## IOE
Impact Outcome Evaluation (IOE)
Project Manager/Main Point of Contact: Amanda Linares (amlinares@ucanr.edu, 916-200-5188)
Activities | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
Planning | Aug: Gray cells denote all months for activity; X denotes a deadline.
Engage intervention site(s); any school or school-based afterschool serving grades 4-12 | bar: Aug to Sept; May to Jul
Attend EATS Survey Administration training (annually) | bar: Aug; Jul
Provide Amanda with a completed Planning Worksheet to receive school-specific EATS online pre/post links | bar: Aug to Oct; Jul
Prior to Pre-testing | Aug: Gray cells denote all months for activity; X denotes a deadline.
Send home Parent Opt Out Forms 2 weeks prior to pre-testing | bar: Aug to Oct
Pre-testing | Aug: Gray cells denote all months for activity; X denotes a deadline.
Administer EATS with at least 2 classrooms of students per school (goal = 30 matched pre/post-tests in each school) | bar: Aug to Oct
Intervention Implementation | Aug: Gray cells denote all months for activity; X denotes a deadline.
Conduct intervention | bar: Sept to May
Post-testing | Aug: Gray cells denote all months for activity; X denotes a deadline.
Administer EATS to all students who received the pre-test | bar: Apr to Jun
Data Entry | Aug: Gray cells denote all months for activity; X denotes a deadline.
If EATS online was used, there will be no data entry; if paper surveys were used, pre-tests should be entered into the school-specific survey links | bar: Aug to Oct
If EATS online was used, there will be no data entry; if paper surveys were used, post-tests should be entered into the school-specific survey links | bar: Apr to Jun
End of Year (June 30th) Deliverables | Aug: Gray cells denote all months for activity; X denotes a deadline.
To Amanda: 1) Pre/post tests entered online (for paper) 2) Planning Workshseet with updates (accurate pre/post dates and opt out data) | bar: Jun

## Adult Direct Ed Evaluation
Adult Direct Education Evaluation
Project Manager/Main Point of Contact: Amanda Linares (amlinares@ucanr.edu, 916-200-5188)
Activities | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Yearly Survey Closure/Downtime | Sept: Gray cells denote all months for activity; X denotes a deadline.
The CalFresh Healthy Living Adult Survey closes annually on 8/31 and does not reopen until the first day of PEARS (mid-October). Evaluation does not need to occur for any direct education in this closure period. | bar: Sept
Planning | Sept: Gray cells denote all months for activity; X denotes a deadline.
Attend Survey Administration training (annually) | bar: Sept
Enter Program Activity* into PEARS before administering Pre-test
Pre-testing, Intervention Implementation, Post-testing | Sept: Gray cells denote all months for activity; X denotes a deadline.
Administer the CalFresh Healthy Living Adult pre-test before delivering a direct education series of four or more sessions
Administer direct education series of four or more sessions over at least four weeks.
Administer the CalFresh Healthy Living Adult post-test after delivering a direct education series of four or more sessions
Data Entry | Sept: Gray cells denote all months for activity; X denotes a deadline.
If online CalFresh Healthy Living Adult Survey was used, there will be no data entry; if paper surveys were used, pre/post-tests should be entered into Survey123 by Aug 31st. | bar: Oct to Aug
End of Year (August 31st) Deliverables | Sept: Gray cells denote all months for activity; X denotes a deadline.
To Amanda: 1) Pre/post tests entered online (for paper) | bar: Aug
*Series-based direct education should only utilize one program activity ID (i.e., sessions are batched in a single entry). Surveys cannot be matched without matching Program Activity IDs at pre- and post-test.